## POC Planning
POC Planning | [7 empty] | Task in Progress | [5 empty] | Task Completed
[7 empty] | 2023-05-05 |  |  |  |  | 2023-05-12 |  |  |  |  | 2023-05-19 |  |  |  |  | 2023-05-26 |  |  |  |  | 2023-06-02 |  |  |  |  | 2023-06-09 |  |  |  |  | 2023-06-16 |  |  |  |  | 2023-06-23 |  |  |  |  | 2023-06-30 |  |  |  |  | 2023-07-07 |  |  |  |  | 2023-07-14 |  |  |  |  | 2023-07-21 |  |  |  |  | 2023-07-28 |  |  |  |  | 2023-08-04 |  |  |  |  | 2023-08-11 |  |  |  |  | 2023-08-18
PROJECT START DATE | 2023-05-01 |  | SCROLL TO WEEK # |  | 1
| Iteration Plan | Start | Target date | Duration | Status | % Complete | time axis 2023-05-01 to 2023-08-18
 | time axis 2023-05-01 to 2023-08-18
ETP Headless Application |  | 2023-05-29 | 2023-06-30 | 25 day(s) |  | 19.64%
Code Reading |  | 2023-05-29 | 2023-06-02 | 5 day(s) |  | 100%
Building GitHub Repo |  | 2023-06-05 | 2023-06-09 | 5 day(s) |  | 100%
Research WITSMLStudio Documentations |  | 2023-06-12 | 2023-06-16 | 5 day(s) |  | 75%
Research ETP Documentations |  | 2023-06-19 | 2023-06-24 | 5 day(s) |  | 0%
Research Automation Technology |  | 2023-06-24 | 2023-06-30 | 5 day(s) |  | 0%
Resolving Connection (Core) functions | [5 empty] | 0%
Resolving Discovery functions | [5 empty] | 0%
Resolving Store functions | [5 empty] | 0%
Resolving Streaming functions | [5 empty] | 0%
Store Notifitcation | [5 empty] | 0%
Growing Object | [5 empty] | 0%
JSON Message | [5 empty] | 0%
Build Headless Application | [5 empty] | 0%
Verify final builds | [5 empty] | 0%
UI Export Parameters Tool |  | 2023-05-29 | 2023-06-30 | 25 day(s) |  | 29.17%
Code Reading |  | 2023-05-29 | 2023-06-02 | 5 day(s) |  | 100%
Adding UI |  | 2023-06-12 | 2023-06-16 | 5 day(s) |  | 45%
Reading Parameters |  | 2023-06-19 | 2023-06-24 | 5 day(s) |  | 30%
Export to File Functions |  | 2023-06-24 | 2023-06-30 | 5 day(s) |  | 0%
Building UI Parameter Tool | [5 empty] | 0%
Verify final builds | [5 empty] | 0%
Messages Validation Tool |  | 2023-06-03 | 2023-06-09 | 5 day(s) |  | 33.33%
Code Reading |  | 2023-06-03 | 2023-06-09 | 5 day(s) |  | 100%
Message Comparing Functions | [5 empty] | 0%
Building Messages Validation Tool | [5 empty] | 0%
Automation Framework |  | 2023-05-29 | 2023-06-30 | 25 day(s) |  | 75%
Building Unit Test Framework |  | 2023-05-29 | 2023-06-02 | 5 day(s) |  | 100%
Reporting Functions |  | 2023-06-12 | 2023-06-16 | 5 day(s) |  | 100%
CICD Integration |  | 2023-06-24 | 2023-06-30 | 5 day(s) |  | 100%
CICD Reporting | [5 empty] | 0%
Automation Test Cases |  | 2023-05-29 | 2023-06-02 | 5 day(s) |  | 33.33%
Review 9 Manual Test Cases |  | 2023-05-29 | 2023-06-02 | 5 day(s) |  | 100%
Implement 9 Automated Test Cases for POC | [5 empty] | 0%
Verify Test Runs | [5 empty] | 0%
POC | [5 empty] | 0%
Documentations | [5 empty] | 0%
Presentations | [5 empty] | 0%
Reviews | [5 empty] | 0%